## List
Impact of 2014 HMIS Standards on reports |  |  | Updated: | 2015-01-07 09:28
How to use: "Updated Report Name" column will indicate the new report name, once report has been updated. Priority column indicates the order in which reports will be updated.
Color coding:No shading=report is waiting for further updates Red shading=report is under development Green shading=not impacted Blue shading=fully updated Grey shading=report to be removed
Bowman/CHIN report | Order | Report name | Updated Report Name - if there is no name in this column, the report has not been updated | Impacted by upgrade / standards | Priority | Notes / approval from Data Committee | Date report has been updated | Notes | Notes on update | Estimated date of update
Bowman/CHIN | 3 | 0252 Data Completeness Report Card v6 C2 | 0252 - Data Completeness Report Card (EE) - v9 C1 not fully updated to 2014 Standard | yes | 1 | Bowman updated to upgrade, CHIN updated (DK, % missing, Exit Dest tab on hold) |  | Partially updated on 10/7: 0252 - Data Completeness Report Card (EE) - v8 C1. Only single report updated (monthly version not updated yet). DK and % missing columns and Exit destination tab not added; veteran question not fully updated | CHIN to make cosmetic updates AFTER Bowman releases next update | TBD-waiting on Bowman
CHIN/Bowman | 51 | 0252 - Data Completeness Report Card (EE) - v6 C2 for CoC | 0252 - Data Completeness Report Card (EE) for CoC - v9 C1 not fully updated to 2014 Standards | yes | 1 |  |  | Partially updated: 0252 - Data Completeness Report Card (EE) for CoC - v8 C1 (10/7/14). DK and % missing columns and Exit destination tab not added; veteran question not fully updated | CHIN to make cosmetic updates AFTER Bowman releases next update | TBD-waiting on Bowman
CHIN |  | Passage Home SSVF GPD custom report |  |  |  | IN DRAFT FOLDER |  | Dec 22 in DRAFT folder | created custom report
Bowman/CHIN |  | HMIS APR modified for CHIN use | [5 empty] | Dec 22 in CHIN staff folder for testing
CHIN | 66 | RAW_Client_Entries_and_Exits_By_Provider_C 1 | RAW_Client_Entries_and_Exits_By_Provider_C 1.3 |  |  |  |  | Jan 5 moved to Raw Data folder | added new HUD fields
CHIN | 68 | RAW_Client_Entries_By_Provider_C 1 | RAW_Client_Entries_By_Provider_C 1.3 |  |  |  |  | Jan 5 moved to Raw Data folder | added new HUD fields
CHIN | 67 | RAW_Client_Entries_and_Interims_By_Provider_C 1 | RAW_Client_Entries_and_Interims_By_Provider_C 1.3 |  |  |  |  | Jan 5 moved to Raw Data folder | added new HUD fields
CHIN | 69 | RAW_Client_Entries_Interims_Exits_By_Provider_C 1 | RAW_Client_Entries_Interims_Exits_By_Provider_C 1.3 |  |  |  |  | Jan 5 moved to Raw Data folder | added new HUD fields
CHIN | 70 | RAW_Client_Profile_By_Provider_C 1 | RAW_Client_Profile_By_Provider_C 1.3 |  |  |  |  | Jan 5 moved to Raw Data folder | added new HUD fields
CHIN | 36 | (Community Link) Mecklenburg United Way by Agencies with County filter-Draft | Mecklenburg United Way by Agencies with County filter C 1.1 | yes |  |  |  | Dec 29 updated and moved to Custom/Mecklenburg/Community Link folder | keep report - swap out veteran status field
CHIN | 58 | CAPER Supplemental | Wake CoC Demographics Report C1.0 | NA |  |  |  | Dec 29 updated and moved to Custom/Wake folder | change title to disassociate from CAPER
CHIN | 18 | HBA Demographics Report v1 | HBA Demographics Report C 1.1. | yes |  |  |  | Dec 29 updated and moved to Custom/Agency Specific folder | keep report
CHIN | 41 | Mecklenburg United Way by Agencies-Draft | Mecklenburg United Way by Agencies C 1.1 | yes |  |  |  | Dec 29 updated and moved to Custom/Mecklenburg folder | keep report - swap out veteran status field
CHIN | 42 | Mecklenburg United Way by Programs-Draft | Mecklenburg United Way by Programs C 1.1 | yes |  |  |  | Dec 29 updated and moved to Custom/Mecklenburg folder | keep report - swap out veteran status field
Bowman | 1 | APR - HUD CoC APR - v22 C1.1 | 0625 - HUD CoC APR - v25C1 | yes |  |  | 2014-12-10 | Dec 8 Bowman released new version, Oct Bowman updated to 2014 Data Dictionary and upgrade
Bowman | 2 | CoC Apr Detail - v18 C1.3 | 0631 - CoC APR Detail - v21 C1 | yes |  |  | 2014-12-10 | Dec 8 Bowman released new version, Oct Bowman updated to 2014 Data Dictionary and upgrade
CHIN | 5 | Enrolled Clients Count v C1.1. |  | yes |  |  | 2014-10-05
CHIN | 65 | Enrolled Clients Report for CoC and Reporting Groups v C1 |  | yes |  |  | 2014-10-05
CHIN | 4 | Enrolled Clients Count with Time in Program v C1 | Enrolled Clients Count with Time in Program v C1.1 | no |  |  | 2015-01-06 | swap out veteran status field
CHIN |  | Monthly Enrolled Clients Count with Time in Program by CoC v C1 | Monthly Enrolled Clients Count with Time in Program by CoC v C1.1 | no |  |  | 2015-01-06 | swap out veteran status field
CHIN |  | Monthly Enrolled Clients Count with Time in Program v C1 | Monthly Enrolled Clients Count with Time in Program v C1.1 | no |  |  | 2015-01-06 | swap out veteran status field
CHIN | 32 | Community Link Exit Data v2 |  | no |  |  | NA | Nov 6 moved to 1-UNTESTED AFTER UPDATE-Do not use | keep report
CHIN | 35 | Enrolled Client Report-Community Link County of Last Perm Address |  | no |  |  | NA | Nov 6 moved to 1-UNTESTED AFTER UPDATE-Do not use | keep report
CHIN | 48 | DEC Clients Served Report - w/ casenotes | no update needed | no |  |  | NA | report not removed per Data Com
CHIN | 49 | DEC Clients Served Report v3.1 | no update needed | no |  |  | NA | report not removed per Data Com
CHIN | 50 | ROI Report by Agency | no update needed | no |  |  | NA
CHIN | 53 | EAN DQ - DRAFT |  | no |  |  | NA | not impacted by upgrade
CHIN | 71 | RAW_Client_Entries_and_Exits_By_ProviderGroup_C 1 |  | no |  |  | NA | no longer impacted, Bowman mapped Vet question
CHIN | 72 | RAW_Client_Entries_and_Interims_By_ProviderGroup_C 1 |  | no |  |  | NA | no longer impacted, Bowman mapped Vet question
CHIN | 73 | RAW_Client_Entries_By_ProviderGroup_C 1 |  | no |  |  | NA | no longer impacted, Bowman mapped Vet question
CHIN | 74 | RAW_Client_Entries_Interims_Exits_By_ProviderGroup_C 1 |  | no |  |  | NA | no longer impacted, Bowman mapped Vet question
CHIN | 85 | Basic Veteran Count of Enrolled Clients with Zip DRAFT |  | no |  |  | NA | no longer impacted, Bowman mapped Vet question
CHIN | 86 | GPD Community Contract Invoice Report - all versions | no update needed | no |  |  | NA
CHIN | 87 | Veteran counts |  | no |  |  | NA | no longer impacted, Bowman mapped Vet question
CHIN/Bowman |  | 3. 0123 - ServicePoint User Last Login Report - v11.06.28 - 2013.10.27 | no update needed | no |  |  | NA
CHIN |  | Program Exit (Enrolled) Previous Year | no update needed | no |  |  | NA
CHIN |  | Program Exit (Served) Previous Year | no update needed | no |  |  | NA
CHIN | 7 | CRIS-Clients Served in Catawba Count | no update needed | no |  |  | NA |  | keep report
CHIN | 8 | CRIS-Users activity report for Catawba county only | no update needed | no |  |  | NA |  | keep report
CHIN | 9 | ECCCM Counseling Survey Exit Data | no update needed | no |  |  | NA |  | keep report
CHIN | 10 | ECCCM Counseling | no update needed | no |  |  | NA |  | keep report
CHIN | 11 | ECCCM Payment Pending Report | no update needed | no |  |  | NA |  | keep report
CHIN | 12 | ECCCCM Poverty Free Lunch Raw Data | no update needed | no |  |  | NA |  | keep report
CHIN | 13 | (ECCCM) Goals and Case Notes Reports Draft | no update needed | no |  |  | NA |  | keep report
CHIN | 14 | Weekly ECCCM Payment Pending Report | no update needed | no |  |  | NA |  | keep report
CHIN | 19 | Report for Lola UMD | no update needed | no |  |  | NA |  | keep report
CHIN | 25 | SAG EFA clients DRAFT | no update needed | no |  |  | NA |  | keep report
CHIN | 31 | Cardinal Innovations YTD Open Cases Draft | no update needed | no |  |  | NA |  | keep report
CHIN | 33 | Community Link Lease Signing Report DRAFT | no update needed | no |  |  | NA |  | keep report
CHIN | 34 | Community Link YTD Open Cases Draft | no update needed | no |  |  | NA |  | keep report
CHIN | 37 | UMC - Services with no ROI | no update needed | no |  |  | NA |  | keep report
CHIN | 43 | (Custom) Banned Clients Report Draft | no update needed | no |  |  | NA |  | keep report
CHIN | 54 | ECCCM Counseling Survey Entry Data | no update needed | no |  |  | NA |  | keep report
CHIN | 57 | Variable Funding Source Report UMC | no update needed | no |  |  | NA |  | keep report
CHIN |  | Charlotte Meckelenburg Coordinated Assessment Report | [5 empty] | withdrawn for timing/funding reasons
CHIN | 22 | Agency beds by program | no update needed | no |  |  | NA |  | test report-not used
CHIN | 26 | Servant Ctr NCHFA Qualified Tenant Role |  | no |  |  | NA | Nov 6 moved to 1-UNTESTED AFTER UPDATE-Do not use | not used-per agency
CHIN | 24 | Housing Costs vs Income Women's Center DRAFT |  | yes |  |  |  | Nov 6 moved to 1-UNTESTED AFTER UPDATE-Do not use | not used-per agency
CHIN | 44 | DEC Age, Gender, household Errors V1 | 0220 - Data Incongruity Locator - Age, Gender, Household Relationship Issues - v5 | yes |  |  |  | Nov 7REPLACED with Bowman 0220 Data Incongruity Locator Age, Gender etc
CHIN | 45 | DEC Clients Created Report v3.1 | removed | yes |  |  | 2014-10-02 | removed
CHIN | 46 | DEC Clients Enrolled Report - V3.2 with casenotes | removed | yes |  |  | 2014-10-02 | removed
CHIN | 47 | DEC Clients Enrolled Report V3.2 | removed | yes |  |  | 2014-10-02 | removed
CHIN/Bowman |  | 0252 Monthly Data Completeness Report Card - v6 C2 for CoC | 0252 - Data Completeness Report Card (EE) for CoC - v9 C1 (for previous 365 days) not fully updated to 2014 Standards | yes |  |  | 2014-10-02 | removed
CHIN/Bowman |  | Single Month Data Completeness Report Card (EE) - v6 C2 for CoC | removed | yes |  |  | 2014-10-02 | remoed
CHIN/Bowman |  | Monthly Data Completeness Report Card (EE) - v6 C2 | removed | yes |  |  | 2014-11-07 | removed
CHIN |  | Monthly DEC Clients Created Report v3.1 | removed | yes |  |  | 2014-10-02 | removed
CHIN |  | Monthly DEC Clients Enrolled Report v3.2 | removed | yes |  |  | 2014-10-02 | removed
CHIN |  | Monthly DEC Clients Served Report v3.1 | removed | no |  |  | 2014-10-02 | removed
CHIN/Bowman |  | Single Month Data Completeness Report Card (EE) - v6 C2 | removed | yes |  |  | 2014-10-02 | removed
CHIN | 6 | Asheville CDBG by Agency |  | yes |  |  | 2014-11-06 | moved to 1-UNTESTED AFTER UPDATE-Do not use | not used-per CoC
CHIN | 23 | Forsyth Futures - raw data enrolled |  | yes |  |  | 2014-11-06 | moved to 1-UNTESTED AFTER UPDATE-Do not use | not used-per CoC
CHIN | 16 | GUM Veterans and EA Costs |  | yes |  |  | 2014-11-06 | moved to 1-UNTESTED AFTER UPDATE-Do not use | not used-per agency
CHIN | 15 | (GUM) 0 A Weekend Report | no update needed | no |  |  | NA |  | not used-per agency
CHIN | 39 | Enrolled Clients Report-MeckHSS DQ Check DRAFT | no update needed | no |  |  | NA |  | project discontinued
CHIN | 40 | MeckHSS HUD Goals and Agency Outcomes DRAFT | no update needed | no |  |  | NA |  | project discontinued
CHIN | 56 | (Guilford) Monthly Variable Funding Source Report | no update needed | no |  |  | NA |  | not used per CoC | 0
CHIN | 27 | UW Draft Report for High Point |  | yes |  |  | 2014-11-06 | moved to 1-UNTESTED AFTER UPDATE-Do not use | not used per CoC
Bowman | 52 | 0252 - Data Completeness Report Card (EE) - v6 with User Creating Prompt |  | NA |  |  | 2014-10-07
CHIN |  | (SSVF) Enrolled Clients Count with Time in Program v C1 First of Month |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
Bowman | 59 | 0252 Data Completeness Report Card for NOFA Project Renewals | 0252 Data Completeness Report Card for NOFA Project Renewals vC1 (Option B) | NA |  |  | 2014-11-07 | Oct 6 updated to work with new picklists, Nov 7 moved to 1-UNTESTED AFTER UPDATE-Do no use
Bowman | 28 | 0615 - HPRP QPR with Client Detail v10.06.02 (old HPRP report) |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
Bowman | 29 | 0623 - HUD HPRP APR - v8 - Released (old HPRP report) |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
Bowman | 80 | 0623 - HUD HPRP APR for SSVF - v 14 |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
Bowman | 81 | 0624 - HPRP APR Detail for SSVF - v11 |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
Bowman | 62 | 0630 - Sheltered-Unsheltered PIT 2014 - v9 |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
Bowman | 60 | 0635 - 2013 NOFA CoC Application Section 2D - v7 |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
Bowman | 61 | 0636 - Project Participant 5A-5B NOFA 2013-2014 - v2 |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
CHIN | 83 | Basic Veteran Count of Enrolled Clients with Chronic CLIENT INFO INCLUDED DRAFT |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
CHIN | 84 | Basic Vetern Count of Enrolled Clients with Chronic DRAFT |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
CHIN | 63 | Chronic counts by CoC or Provider Group |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
CHIN | 64 | Chronic counts by program |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
CHIN | 65 | Chronically Homeless Exit Destination with counts by Provider Group for clients |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
CHIN | 82 | Enrolled Clients Report SSVF with military service info v C2 |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
CHIN | 55 | GSO Emergency Assistance DQ Report -DRAFT |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
CHIN | 17 | HBA Demographics Report |  | yes |  |  | 2014-11-06 | moved to 1-UNTESTED AFTER UPDATE-Do not use
CHIN | 30 | HPRP Services |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
Bowman | 75 | Monthly Data Completeness Report Card for SSVF |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
Bowman | 77 | Monthly Followup Data Completeness Report Card for SSVF |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
Bowman | 76 | Monthly Follow-up HPRP Data Quality Report Part 1 for SSVF |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
Bowman | 78 | Monthly HPRP Data Quality Report Part 1 for SSVF |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
CHIN/Bowman |  | SSVF Data Completeness Followup Monthly Report Card |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use
CHIN | 20 | UMD Meals Report DRAFT v9.24.10 |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use | not used-per agency
CHIN | 21 | UMD Meals Report DRAFT v9.24.10 NO COMMUNITY CLIENT INFO |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use | not used-per agency
Bowman | 79 | 0230 - HPRP Data Quality Report Part 1 - v11 edited to run for SSVF |  | NA |  |  | 2014-11-07 | moved to 1-UNTESTED AFTER UPDATE-Do not use