## Sheet1
Transtion Budget (Budget Type Ongoing Services)
Task and Activities: | Hours | Estimated Costs | Staff Responsible | Completion Date
Governance | 60 | 4200 | Barb/Eric | 2015-04-30
-Interim Budget
-Interim MOU
-Year 1 Budget Finalized
-Reporting P&P Finalized
-Year 1 Contract
-HMIS Policies and Procedures
Communication Plan | 15 | 900 | Gerry | 2015-01-31
-Develop Calendar of Governance Meetings
-Negotiate content for initial LSA Meetings
-Develop Calendar for LSA & User Meetings
-Develop Calendar of Trainings (See Training)
-Develop Communications Contact Lists
Privacy Plan | 40 | 7800 | Barb | 2015-04-30
-NC Consultant Fees |  | 5000
-Negotiation/Approval of new Privacy Plan | 10
-Develop Revised Agreements (Partiicpation, QSOBAA, etc) | 20
-Develop Client Releases / Notices ect | 10
System Tasks (mix of Bowman and MCAH) | 117 | 21020 | Mixed | 2015-06-30
-Update Contract with Bowman (MCAH & Goveranance) | 5 |  | Barb
-Server Evaluation (Bowman) |  | Normally Free
-Evaluate and add new Modules | 4 |  | Gerry
-Develop / Approve Archive & Data Reorgainization Plans | 20 |  | Shanna/Jill
-SOWs with Bowman (Archive, move data and Reports) | 8 | 10000 | Gerry/Barb
-Build / modify Reports on NCHMIS @ $110/hr | 80 |  | Shanna/Barb
Training (MCAH Staff) | 143 | 8960 | Mixed | 2015-05-31
-Administrative Pages (20 1 hour Sessions) | 25 |  | Gerry
-Visibility and Security (20 1 hour Sessions) | 25 |  | Gerry
-Module Training (current and new - Live via WEB/Recorded) | 30 |  | Team
-Privacy (20 hrs Live on-Site and Live via WEB) | 28 |  | Barb
-Help Desk related to above training (Jan to April) | 25 |  | HMIS Team
-Reports (5 1 hour Sessions) | 10 |  | Shanna
On Site Staffing (Mid March to June 30th) |  | 76584.125 | Mixed | 2015-06-30
-Recruiting | 30 | 1550 | Eric/Barb/Gerry | 2015-02-28
-1 Staff FTE (mid-March to June 30) |  | 23625
-Office Expenses + Equipment & Supplies |  | 7291.6667 |  | April ongoing
- Equipment (2 computers, 1 printer, 1 tablet, 2 headsets) |  | 4100
-Internet + GoToMeeting+Office Supplies |  | 3837.4583
-Visiting MCAH Staff (April to June includes Housing/Car Stipend) |  | 36180 | Gerry
Travel Expenses (Air+Hotel+Car) |  | 12103 | Mixed | 2015-06-30
-Jan (1 trip, 2 staff, 2.5 days) |  | 1958
-Feb (1 trip, 2 staff, 5 days) - Interviews + meetings |  | 2729
-Mar (1 5-day trip, 1 staff to NC, 1 5-day trip NC staff to Michigan) |  | 2729
-April (1 trip 2 staff, 5 days) |  | 2729
-May (1 trip 1 staff, 2.5 days) |  | 1958
Administrative (Jan to April) |  | 7500 |  | 2015-04-30
-Payroll & Budget & Executive Director | 45 | 2700 | Eric & Chris
-Planning and Governance Meetings | 80 | 4800 | Barb/Eric/Gerry
Full Support Operations beginning on May 1,2015 (2 months) |  | 20160.645 | Mixed | May ongoing
-Training Development and initial training delivery (front loaded) |  | 6123.12
-Help Desk (prorated from Annual Budget) |  | 3126.24
-Project Based Admin Support (2 months) |  | 6604.015
-Insurance, audit, payroll, financial services, licenses (front loaded) |  | 4307.27
Grand Total: |  | 159227.77 |  | 2015-06-30
Notes (See Application Budget for Detail on Expenses):
-Hourly Rates: Barb @ $70/hr, Analyst Wk @$110/hr, All other at $60/hour
-$10,000 Bowman and $5,000 for Privacy Expert were included.
-$81,000 Salary + Benefits prorated.
-Staff and Space Costs were prorated from the 25k estimate in Application budget
-Travel Expenses were based on historical costs using NC Per Diem
-Jan. travel in Contract Extention. Any additional trips will be negotiated on a cost/trip basis.
-Training will be intensive the first 4 months. $9120 was split - half in May and June. $9360 prorated
0