## NC Budget v6
MCAH NC Transtion Budget (Budget Type Ongoing Services)
Task and Activities: | Hours | Estimated Costs | Staff Responsible | Completion Date
Governance | 60 | 4200 | Barb/Eric | 2015-04-30
-Interim Budget
-Interim MOU
-Year 1 Budget Finalized
-Reporting P&P Finalized
-Year 1 Contract
-HMIS Policies and Procedures
Communication Plan | 15 | 900 | Gerry | 2015-01-31
-Develop Calendar of Governance Meetings
-Negotiate content for initial LSA Meetings
-Develop Calendar for LSA & User Meetings
-Develop Calendar of Trainings (See Training)
-Develop Communications Contact Lists
Privacy Plan | 40 | 7800 | Barb | 2015-04-30
-NC Consultant Fees |  | 5000
-Negotiation/Approval of new Privacy Plan | 10
-Develop Revised Agreements (Particpation, QSOBAA, etc) | 20
-Develop Client Releases / Notices etc | 10
System Tasks (mix of Bowman and MCAH) | 77 | 16750 | Mixed | 2015-06-30
-Update Contract with Bowman (MCAH & Governance) | 5 | 350 | Barb
-Server Evaluation (Bowman) |  | Normally Free
-Evaluate and add new Modules | 4 | 240 | Gerry
-Develop / Approve Archive & Data Reorganization Plans | 20 | 1200 | Shanna/Jill
-SOWs with Bowman (Archive, move data and reports) | 8 | 10560 | Gerry/Barb
-Build / modify Reports on NCHMIS @ $110/hr | 40 | 4400 | Shanna/Barb
Training (MCAH Staff) | 123 | 7460 | Mixed | 2015-05-31
-Administrative Pages (20 1 hour Sessions) | 25 |  | Gerry
-Visibility and Security (20 1 hour Sessions) | 25 |  | Gerry
-Module Training (current and new - Live via WEB/Recorded) | 30 |  | Team
-Privacy (8 hrs Live via WEB) See April for on-site | 8 |  | Barb
-Help Desk related to above training (Jan to April) | 25 |  | HMIS Team
-Reports (5 - 1 hour Sessions via Web) | 10 |  | Shanna
On Site Staffing (Mid March to June 30th) |  | 79677.4583 | Mixed | 2015-06-30
-Recruiting | 13 | 810 | Eric/Barb/Gerry | 2015-02-28
-1 Staff FTE (mid-March to June 30) |  | 23625
-.5 Staff FTE (April - June 30) |  | 3833.3333
-Office Expenses + Equipment & Supplies |  | 7291.6667 |  | April ongoing
- Equipment (2 computers, 1 printer, 1 tablet, 2 headsets) |  | 4100
-Internet + GoToMeeting+Office Supplies |  | 3837.4583
-Visiting MCAH Staff (April to June includes Housing/Car Stipend) |  | 36180 | Gerry
Travel Expenses (Air+Hotel+Car+Hours Spent on Site) |  | 20901.75 | Mixed | 2015-06-30
-Jan (1 trip, 2 staff, 2.5 days) Travel Expenses |  | 1761 | Barb/Gerry
-On Site Staff hrs for Barb and Gerry | 32 | 2080
-Feb (Barb 2 trips 2 days; Gerry 2 trips, 3 days ) - Governance + Interviews |  | 2988 | Barb/Gerry
- Total 5 days - 40 hours (Barb 16, Gerry 24) | 40 | 2560
-Mar (1 5-day trip, 1 staff to NC, 1 5-day trip NC staff to Michigan) |  | 3041.5 | Gerry/New
-Michigan on-site hrs = 40, New hire billed elsewhere | 40 | 2400
-April (1 trip 5 days) Barb - Gerry is housed in NC. |  | 1270.75 | Barb
- Barb meets w each CoC & trains privacy | 40 | 2800
-May (1 trip 1 staff, 2.5 days) (Gerry is housed in NC) |  | 880.5 | Mixed
-Barb at Governance Meeting | 16 | 1120
Administrative (Jan to April) |  | 7500 |  | 2015-04-30
-Payroll & Budget & Executive Director | 45 | 2700 | Eric & Chris
-Planning and Governance Meetings | 80 | 4800 | Barb/Eric/Gerry
Full Support Operations beginning on May 1,2015 (2 months) |  | 20160.645 | Mixed | May ongoing
-Training Development and initial training delivery (front loaded) |  | 6123.12
-Help Desk (prorated from Annual Budget) |  | 3126.24
-Project Based Admin Support (2 months) |  | 6604.015
-Insurance, audit, payroll, financial services, licenses (front loaded) |  | 4307.27
Grand Total: |  | 165349.8533 |  | 2015-06-30
Notes (See Application Budget for Detail on Expenses):
-Hourly Rates: Barb @ $70/hr, Analyst Wk @$110/hr, All other at $60/hour
-$10,000 Bowman and $5,000 for Privacy Expert were included.
-$81,000 Salary + Benefits prorated.
-Staff and Space Costs were prorated from the 25k estimate in Application budget
-Travel Expenses (8 hrs per day per staff, Airfare estimated at $450,Car Rental = $50/day + .55/mile mileage (assumes 25 miles rtrp to airport), hotel per diem=$97/day, food/expenses perdiem = $56/day. Travel day is .75 day.
-Any additional trips will be negotiated on a cost/trip basis.
-Training will be intensive the first 4 months. $9120 was split - half in May and June. $9360 prorated