## Timeline
Documents | Responsible Entity | Decisions | Timeline to Send to GC for Review | Timeline for Approval | Timeline for Implementation | Internal Comments/Notes
Annual Contract | Tim/Darryl | • Example A • Example B | 2015-07-13 | 2015-08-10 | 2015-09-30 | The annual contract is now October 1 - June 30
Scope of Work | Eric |  | 2015-07-13 | 2015-08-10 | 2015-09-30 | This is the annual SOW for October 1 to June 30. The Budget workgroup will further discuss this with Eric on 7/20 meeting
Budget | Eric |  | Already Approved | Already Approved | Already Approved
Consider Budget format | Denise/Eric |  | 2015-07-13 | 2015-08-10 | 2015-09-30 | Denise to make sure categories are broken down for HUD categorization; Denise will work on this and then share subtasks with workgroup
Cost Share | Denise |  | 2015-07-13 | 2015-08-10 | 2015-09-30 | GC already determined cost-share percentages; the Budget workgroup just needs to outline the dollar amounts each CoC is responsible for
Reports and Reimbursement Procedures | TBD |  | 2015-07-13 | 2015-08-10 | 2015-09-30
Annual MOU | Heather |  | 2015-07-13 | 2015-08-10 | 2015-09-30