## CoC Eval Process Checklist
HMIS@NCCEH Implementation
Continuum of Care Evaluation Process Checklist
Checklist Item | Information | Met
Continuum of Care Information
Hold initial call with CoC to define process
Identify top applicant goals in joining the HMIS@NCCEH HMIS implementation
Email information request to CoC Lead
Number of providers using HMIS
Number of licensed HMIS users
Copy of CoC Governance Charter
Copy of most recent Housing Inventory Count
Copy of current CoC's HMIS Policies and Procedures
Copy of current CoC's HMIS Privacy Policy
Current HMIS Funding Sources
Current FTE CoC HMIS staff
Current CoC HMIS staff job description/workplan/responsibilities
Projected CoC designees to the HMIS Advisory Board
Minutes authorizing NCCEH as the HMIS Lead
| Information | Met
HMIS Lead Agency Admin
Determine staff capacity changes needed to add new CoC
Reach out to WellSky to determine contract increases
Draft projected budget to add new CoC
Identify maximum of 5 HMIS super users
Provide access to training site for 14 days for identified CoC super users
Schedule and meet with CoC CE Lead staff to provide a CE demo
Schedule and meet with CoC Lead to discuss budget, answer questions, and layout process
Identify and address potential challenges between CoC/implementation expectations
Finance and Operations Director phone call with CoC Lead to discuss contracting
Contract between CoC Lead Agency and NCCEH
Facilitate HMIS grant ownership to NCCEH
Develop order form with WellSky to import data into HMIS@NCCEH
QA demo site
Negotiate timeline for import and launch
| Information | Met
HMIS Advisory Board Activities
Notify HMIS Advisory Board of CoC request
Present to HMIS Advisory Board Executive Committee to discuss budget implications
Present to HMIS Advisory Board for approval (75% majority vote needed)
Notify CoC of approval/denial
Send Governance Charter to CoCs for signature through DocuSign