## 1-Governance
Goal One: Improve CoC Governance and Structure
Strategy | Action Steps | Person/Organization Responsible | Timeframe | Relevance
|  |  |  | CoC Check-up Elements(s) | FSP Strategy(s) | HEARTH PM(s)
Create a clear mission & vision to govern the NC BoS CoC | Create draft mission & vision statement | CoC Lead (NCCEH) | March 2012 | 1.1
| RC leads take message to RCs for input | Regional Committee Leads | April 2012 | 1.1
| Approve mission & vision statement | BoS Steering Committee | May 1, 2012 | 1.1
| Review and update mission & vision on an annual basis | BoS Steering Committee | January on annual basis | 1.1
Codify Steering Committee governing structure rules | Create draft governing language for Steering Committee | CoC Lead (NCCEH) | March-May 2012 | 1.2, 1.4
| RC leads take message to RCs for input | Regional Committee Leads | June 2012 | 1.2, 1.4
| Approve governing rules for BoS CoC | BoS Steering Committee | July 2012 | 1.2, 1.4
Clarify Roles | Clarify role between the State and NCCEH | DHHS & NCCEH | May 2012 | 1.2.4
| Clarify CoC staff role |  | May 2012 | 1.2.4
| Update CoC MOU with HMIS Lead (CHIN) | CoC Lead (NCCEH) and HMIS Lead (CHIN) | May 2012 | 1.2.5
Create Minimum Requirements for Governing Structure for Regional Committees | Create draft governing language for Regional Committees | CoC Lead (NCCEH) | March-May 2012 | 1.2/1.3/1.4
| RC leads take message to RCs for input | Regional Committee Leads | June 2012 | 1.2/1.3/1.4
| Approve governing rules for regional committees | BoS Steering Committee | July 2012 | 1.2/1.3/1.4
| Ensure Regional Committee meets RC requirements and is implementing new policies & procedures | Regional Committee Leads | July & August 2012 | 1.2/1.3/1.4
Strengthen Subcommittees | Evaluate existing subcommittee structure | BoS Steering Committee | Summer 2012 and then annually in January | 1.3
| Revise subcommittee structure as needed | BoS Steering Committee | Summer 2012 | 1.3
| Increase & diversify subcommittee participation | all members | ongoing | 1.3.1
Diversify Steering Committee membership to include state partners (i.e. VA, NC HFA, DHHS) | Invite state partners to the Steering Committee | CoC Lead (NCCEH) | Summer 2012 | 1.3
| Educate state partners regarding Balance of State CoC structure, purpose, mission | CoC Lead (NCCEH) | Summer 2012 | 1.3.1
Diversify Regional Committee Membership | Outreach to homeless service agencies, local government officials, ESG grantees, and other stakeholders not at the Regional Committee table | Regional Committee Leads | ongoing | 1.3
| ESG grantees regularly participate in Regional Committee meetings | ESG Grantees | ongoing | 1.3
| Educate stakeholders regarding BoS CoC and Regional Committee structure and work | Regional Committee Leads and CoC Lead (NCCEH) | ongoing | 1.3

## 2-Strategic Plan
Goal Two: Create and Adopt CoC Strategic Plan
Strategy | Action Steps | Person/Organization Responsible | Timeframe | Relevance
|  |  |  | CoC Check-up Elements(s) | FSP Strategy(s) | HEARTH PM(s)
Develop BoS strategic plan process & timeline | Secure Funding for Plan Development | CoC Lead (NCCEH) | Spring 2012 | 2.1 | 1c
| Create Planning Committee | CoC Lead (NCCEH) | dependent on funding | 2.1
| Create timeline to determine timeframe for action steps | Planning Committee | dependent on funding | 2.1
| Develop process for creating CoC Strategic Plan | Planning Committee | dependent on funding | 2.1
Review CoC data to create baseline for the plan | Review exisiting data (PIT, AHAR, eHIC, ESG & CoC grantee performance) | Planning Committee | dependent on funding | 2.1.1.4
| Identify Needs & Gaps | Planning Committee | dependent on funding | 2.1.1.4
Gather Input & Create Buy-in from Regional Committees & Other Stakeholders | Identify Stakeholders | Planning Committee | dependent on funding | 2.1.1 | 1b, 1h, 1c
| Hold a meeting to discuss the BoS CoC Strategic Plan | CoC Lead (NCCEH) | dependent on funding | 2.1
| Create communications strategy to educate stakeholders about the plan | Planning Committee | dependent on funding | 2.1
Draft Strategic Plan Document | Create First Draft of CoC Strategic Plan based on meeting input | CoC Lead (NCCEH) | dependent on funding | 2.1
| Gather feedback on Strategic Plan | Planning Committee | dependent on funding | 2.1
| Publish final version of Strategic Plan | CoC Lead (NCCEH) | dependent on funding | 2.1
Adopt & Implement CoC Strategic Plan | Adopt CoC Strategic Plan | BoS Steering Committee | dependent on funding | 2.1 | 10a, 10c, 7b
| Develop implementation timeline | Planning Committee | dependent on funding | 2.3
| Integrate Strategic Plan into all CoC reporting, scorecard, etc. | CoC Lead (NCCEH) | dependent on funding | 2.3 | 2h
| Begin Implementing the plan locally | Regional Committees | dependent on funding | 2.3

## 3-Infrastructure
Goal Three: Improve CoC Infrastructure and Capacity
Strategy | Action Steps | Person/Organization Responsible | Timeframe | Relevance
|  |  |  | CoC Check-up Elements(s) | FSP Strategy(s) | HEARTH PM(s)
Clarify Regional Committee Relationship to grantees | Draft language to clarify role of Regional Lead in assisting grantees | CoC Lead (NCCEH) and BoS CoC Steering Committee members | 2012-07-01 | 3.1 | 7f, 3c
| Approve MOU | Steering Committee | 2012-08-01
Grow capacity of Regional Committees | Identify gaps in Regional Coordination at the local level | Regional Leads and Regional Committee members | Summer 2012 | 3.1
| Ensure that Regional Committee Leads have approval to spend staff time on Regional Committee coordination | Regional Leads with support of CoC Lead (NCCEH) | Fall 2012 | 3.1
| Identify strategies to fill gaps in Regional Committee coordination at the local level | Regional Leads and CoC Lead (NCCEH) | Fall 2012 | 3.1
Grow CoC Lead Capacity | Identify gaps in capacity | ICCHP, CoC Lead (NCCEH) and BoS CoC Steering Committee members | Summer 2012
| Create plan for addressing gaps | ICCHP, CoC Lead (NCCEH) and BoS CoC Steering Committee members | Fall 2012
| Secure funding and make adjustments | ICCHP, CoC Lead (NCCEH) and BoS CoC Steering Committee members | 2013

## 4-HMIS
Goal Four: Improve HMIS Use and Capacity
Strategy | Action Steps | Person/Organization Responsible | Timeframe | Relevance
|  |  |  | CoC Check-up Elements(s) | FSP Strategy(s) | HEARTH PM(s)
Improve the capacity of the CoC to manage the HMIS responsibilities of the CoC | Hold a meeting with CHIN/HMIS Lead regarding roles and responsibilities | CoC and HMIS Leads (NCCEH and CHIN) | 2012-04-01 | 3.3
| Draft new language that clarifies the respective roles of the CoC and the HMIS Lead Agency | CoC and HMIS Leads (NCCEH and CHIN) | 2012-05-01
| Approve new MOU with CHIN | Steering Committee | 2012-06-01
Improve the reporting or otherwise informing the CoC decision-making group of data quality concerns | Hold a meeting with HMIS Lead regarding BoS CoC data quality and process of improvement | CoC and HMIS Leads (NCCEH and CHIN) | 2012-03-01 | 3.3.5.3
| Create process for BoS data quality checks at the regional and BoS level | CoC and HMIS Leads (NCCEH and CHIN) | March & April 2012 | 3.3.5.3
| Regional Leads regularly discuss data quality at the regional level | Regional Leads | 2012-05-01
| Form a data quality subcommittee and meet quarterly to discuss DQ at the BoS CoC level (to include HMIS Lead participation) | CoC Lead (NCCEH) | 2012-04-01 | 3.3.6
Improve the capacity of the HMIS Lead agency to adequately fulfill its responsibilities | Review HMIS Lead responsibilities | CoC and HMIS Leads (NCCEH and CHIN) | 2012-04-01
| Evaluate what capacity needs improvement | CoC and HMIS Leads (NCCEH and CHIN) | Summer 2012
| Conduct end-user and community leaders survey of CHIN | NCCEH | Summer 2012
| Support staffing or fee structure changes (if any) | CoC Lead (NCCEH) | Summer 2012 | 3.3.8.1
Improve utility and usefulness of HMIS data for CoC and participating agencies | Conduct end-user and community leaders survey of CHIN | NCCEH | Summer 2012
| Make adjustments as needed | HMIS Lead (CHIN) | Fall 2012
| Use HMIS to generate reports for use in monitoring and evaluating system and project performance | CHIN users & funders | Fall 2012 | 3.3.17/3.3.18 | 2g
Increase AHAR accepted shells | Training from HMIS regarding how to read AHAR reports | HMIS Lead (CHIN) | Summer 2012 | 3.3.24
| Create plan to increase bed coverage for each AHAR category | CoC and HMIS Leads (NCCEH and CHIN) and Steering Committee | 2012-04-01 | 3.3.23
| Increase HMIS bed coverage | Regional Committees and providers | Beginning April 2012, ongoing | 3.3.23
Use HMIS data to generate reports that meaningfully support CoC planning and project development | Evalauate needs | CoC and HMIS Leads (NCCEH and CHIN) and Steering Committee | Begin in 2013
| Create plan | CoC and HMIS Leads (NCCEH and CHIN) and Steering Committee | Begin in 2013
| Begin using reports | Steering & Regional Committees | Begin in 2013 | 3.3.22
Use BoS HMIS grant to pay for data analysis | Evaluate BoS data analysis needs | CoC Lead (NCCEH) | Fall 2012 |  | 2g
| Create plan for how to meet data analysis needs | CoC and HMIS Leads (NCCEH and CHIN) | Fall 2012
| Begin using BoS HMIS grant for data analysis | CoC Lead and HMIS Lead (NCCEH and CHIN) | 2013-07-01

## 5-Performance
Goal Five: Improve CoC & ESG Grantee Performance
Strategy | Action Steps | Person/Organization Responsible | Timeframe | Relevance
|  |  |  | CoC Check-up Elements(s) | FSP Strategy(s) | HEARTH PM(s)
Provide Education on Evidence-Based Practices | Identify trainging needs | CoC Lead (NCCEH), Regional Leads, and grantees | semi-annually beginning summer 2012 |  | 7b, 2c | C
| Make in-person trainings available to providers | CoC Lead (NCCEH) | ongoing
| Use conference calls and subcommittees to provide training & education | CoC Lead (NCCEH) | ongoing |  | 1a
| Create materials to post online | CoC Lead (NCCEH) | ongoing |  | 1a
Require Grantees to Report on Performance at Regional Committees | Develop reporting format for grantees | CoC Lead (NCCEH) | 2012-05-01
| Regional Committees schedule ESG & CoCs grantees to report on projects at RC meetings on a quarterly basis | Regional Leads | 2012-04-01
| ESG & CoC Grantees present program information based on required format | CoC & ESG Grantees | Ongoing quarterly
| Review and update grantee RC reporting format | CoC Lead (NCCEH) | as needed, minimum annually
Use Quarterly Performance Reports to measure performance on quarterly basis | Complete QPR and submit to NCCEH | CoC grantees | Ongoing quarterly |  |  | C,E
| Review performance check on QPR and make program adjustments as necessary | CoC grantees | Ongoing quarterly
| Review QPRs and provide technical assistance as needed | CoC Lead (NCCEH) | Ongoing quarterly
| Review and Update QPR to reflect HEARTH Performance Measurement Questions | CoC Lead (NCCEH) | After HEARTH CoC Regulations are available |  | 10c | A,B,C,D,E,F,G
Increase understanding and accuracy of HUD Annual Progress Report | Provide APR training | HUD | 2012 |  | 2b
| CoC grantees submit draft APR to NCCEH before | CoC grantees | Ongoing
| Check for accuracy and completeness of APR | CoC Lead (NCCEH) | Ongoing
| Provide technical assistance to grantees completing APRs as necessary | CoC Lead (NCCEH) | Ongoing

## 6-Housing & Services
Goal Six: Improve CoC Housing and Services Capacity
Strategy | Action Steps | Person/Organization Responsible | Timeframe | Relevance
|  |  |  | CoC Check-up Elements(s) | FSP Strategy(s) | HEARTH PM(s)
Improve accessibility of the housing and services in the BoS CoC by persons who are homeless or at-risk of homelessness to improve sufficiency and effetiveness of preventing and ending homelessenss | Inventory housing and services in Regional Committees and create baseline | Regional Committee/ Regional Lead w. support from CoC Lead (NCCEH) |  | 4.1-4.4 |  | all
| Create plan to improve accessibility of housing and services in the BoS CoC at the regional level | Regional Committee/ Regional Lead w. support from CoC Lead (NCCEH) |  | 4.1-4.4 |  | all
| Follow plan and increase housing and services accessibility | Regional Committee/ Regional Lead w. support from CoC Lead (NCCEH) |  | 4.1-4.4 |  | all
Improve the system of integrated housing and services |  |  |  | 4.2
Improve the CoC's knowledge and capacity to provide housing and services | Assess current knowledge and capacity |  |  | 4.4
| Create improvement plan including training and technical assistance |  |  | 4.4
| Implement Plan |  |  | 4.4
Improve access to income supports | Continue SOAR training and support | NCCEH
| Promote SOAR at the local level | Regional Committees
| Dedicate positions or staff time to SOAR | providers |  |  | 6b
Prepare for Medicaid expansion | Research opportunities | NCCEH
| Advocate for targeted resources and adequate service packages | NCCEH with support from communities
| Educate communities | NCCEEH |  |  | 6e
Expand supply of supportive housing | After assessing Needs & Gaps, create supportive housing expansion plan | Steering Committee
| Implement Plan | Regional Committees, providers, CoC Lead & funders |  |  | 4a
Promote best practices in crisis response | Assess current knowledge and capacity | CoC Lead (NCCEH)
| Create improvement plan including training and technical assistance | CoC Lead (NCCEH)
| Implement Plan | all stakeholders |  |  | 10a
Support rental housing subsidies | Inventory current stock and research best practice approaches | CoC Lead (NCCEH) with support from Regional Leads
| Advocate for existing resources to support rental housing subsidies | all stakeholders
| Invest CoC & ESG dollars in rental assistance | grantees, Regional Committee, CoC Lead (NCCEH) |  |  | 3a
Increase availability of behavioral health services | Advocate for medicaid & IPRS funding for tenancy supports | NCCEH with support from communities
| Provide training on working with homeless & at-risk populations to behavioral health providers | DHHS & NCCEH |  |  | 7e
Ensure continuity through HPRP services |  |  |  |  | 10d
Improve access to assistance |  |  |  |  | 3c
Increase service-enriched housing |  |  |  |  | 3d
Coordinate/Integrate employment programs, increase work for veterans |  |  |  |  | 5d, 5e
Inventory Federal emergency response systems |  |  |  |  | 2f
Increase targeted services for persons experiencing homelessness or at-risk of homelessness |  |  |  | 4.1
Improve discharge practices of the hospital, foster care, and correction systems so none of them release into homelessness |  |  |  | 4.1 | 9a
Improve assessment for persons experiening or at-risk of homelessness to provide appropriate housing placement and services |  |  |  | 4.1
Improve temporary shelter in linking persons who are homeless to permanent housing options and resources |  |  |  | 4.1.6.8