## 1-Governance
Goal One: Improve CoC Governance and Structure
Strategy | Action Steps | Person/Organization Responsible | Timeframe | Relevance
|  |  |  | CoC Check-up Elements(s) | FSP Strategy(s) | HEARTH PM(s)
Create a clear mission & vision to govern the NC BoS CoC | Create draft mission & vision statement | CoC Lead (NCCEH) | May 2012 | 1.1 | 10c, 4a, 1b, 2e | A-G
| RC leads take message to RCs for input | Regional Committee Leads | June 2012 | 1.1
| Approve mission & vision statement | BoS Steering Committee | June 5, 2012 | 1.1
| Review and update mission & vision on an annual basis | BoS Steering Committee | January on annual basis | 1.1
Codify Steering Committee governing structure rules | Hold meeting for BoS stakeholders to educate them about governance and structure | NCCEH | Summer 2012 | 1.1
| Create draft governing language for Steering Committee | CoC Lead (NCCEH) | May-June 2012 | 1.2, 1.4
| RC leads take message to RCs for input | Regional Committee Leads | June 2012 | 1.2, 1.4
Clarify Roles | Approve governing rules for BoS CoC | BoS Steering Committee | July 2012 | 1.2, 1.4
| Clarify role between the State and NCCEH | DHHS & NCCEH | May 2012 | 1.2.4
| Clarify CoC staff role |  | May 2012 | 1.2.4
Create Minimum Requirements for Governing Structure for Regional Committees | Update CoC MOU with HMIS Lead (CHIN) | CoC Lead (NCCEH) and HMIS Lead (CHIN) | May 2012 | 1.2.5
| Create draft governing language for Regional Committees | CoC Lead (NCCEH) | April-June 2012 | 1.2/1.3/1.4
| RC leads take message to RCs for input | Regional Committee Leads | July 2012 | 1.2/1.3/1.4
| Approve governing rules for regional committees | BoS Steering Committee | August 2012 | 1.2/1.3/1.4
Strengthen Subcommittees | Ensure Regional Committee meets RC requirements and is implementing new policies & procedures | Regional Committee Leads | August & September 2012 | 1.2/1.3/1.4
| Evaluate existing subcommittee structure | BoS Steering Committee | Summer 2012 and then annually in January | 1.3
| Revise subcommittee structure as needed | BoS Steering Committee | Summer 2012 | 1.3
Diversify Steering Committee membership to include state partners (i.e. VA, NC HFA, DHHS) | Increase & diversify subcommittee participation | all members | ongoing | 1.3.1
| Invite state partners to the Steering Committee | CoC Lead (NCCEH) | Summer 2012 | 1.3
Diversify Regional Committee Membership | Educate state partners regarding Balance of State CoC structure, purpose, mission | CoC Lead (NCCEH) | Summer 2012 | 1.3.1
| Outreach to homeless service agencies, local government officials, ESG grantees, and other stakeholders not at the Regional Committee table | Regional Committee Leads | ongoing | 1.3
| ESG grantees regularly participate in Regional Committee meetings | ESG Grantees | ongoing | 1.3
| Educate stakeholders regarding BoS CoC and Regional Committee structure and work | Regional Committee Leads and CoC Lead (NCCEH) | ongoing | 1.3

## 2-Strategic Plan
Goal Two: Create and Adopt CoC Strategic Plan
Strategy | Action Steps | Person/Organization Responsible | Timeframe | Relevance
|  |  |  | CoC Check-up Elements(s) | FSP Strategy(s) | HEARTH PM(s)
Develop BoS strategic plan process & timeline | Secure Funding for Plan Development | CoC Lead (NCCEH) | Spring/Summer 2012 | 2.1 | 1c | A-G
| Create Planning Committee | CoC Lead (NCCEH) | dependent on funding |  | D | A-G
| Create timeline to determine timeframe for action steps | Planning Committee | dependent on funding |  | D | A-G
| Develop process for creating CoC Strategic Plan | Planning Committee | dependent on funding |  | D | A-G
Review CoC data to create baseline for the plan | Review exisiting data (PIT, AHAR, eHIC, ESG & CoC grantee performance) | Planning Committee | dependent on funding | 2.1.1.4 | D | A-G
| Identify Needs & Gaps | Planning Committee | dependent on funding |  | D | A-G
Gather Input & Create Buy-in from Regional Committees & Other Stakeholders | Identify Stakeholders | Planning Committee | dependent on funding | 2.1.1 | 1b, 1h, 1c | A-G
| Hold a meeting to discuss the BoS CoC Strategic Plan | CoC Lead (NCCEH) | dependent on funding | 2.1 | D | A-G
| Create communications strategy to educate stakeholders about the plan | Planning Committee | dependent on funding |  | D | A-G
Draft Strategic Plan Document | Create First Draft of CoC Strategic Plan based on meeting input | CoC Lead (NCCEH) | dependent on funding |  | D | A-G
| Gather feedback on Strategic Plan | Planning Committee | dependent on funding |  | D | A-G
| Publish final version of Strategic Plan | CoC Lead (NCCEH) | dependent on funding |  | D | A-G
Adopt & Implement CoC Strategic Plan | Adopt CoC Strategic Plan | BoS Steering Committee | dependent on funding |  | 10a, 10c, 7b | A-G
| Develop implementation timeline | Planning Committee | dependent on funding | 2.3 | D | A-G
| Integrate Strategic Plan into all CoC reporting, scorecard, etc. | CoC Lead (NCCEH) | dependent on funding |  | 2h | A-G
| Begin Implementing the plan locally | Regional Committees | dependent on funding |  | D | A-G
| Develop a plan to implement, monitor, and report on progress of strategic plan | CoC Lead (NCCEH) | dependent on funding | 1.1,2.2,2.1 | D | A-G

## 3-Infrastructure
Goal Three: Improve CoC Infrastructure and Capacity
Strategy | Action Steps | Person/Organization Responsible | Timeframe | Relevance
|  |  |  | CoC Check-up Elements(s) | FSP Strategy(s) | HEARTH PM(s)
Clarify Regional Committee Relationship to grantees | Draft language to clarify formal role of Regional Committee (RC) and Regional Lead (RL) in assisting grantees | CoC Lead (NCCEH) and BoS CoC Steering Committee members | 2012-07-01 | 3.1 | 7f, 3c, 4a, 10c | A-G
| Approve MOU between RCs and grantees | Steering Committee | 2012-08-01 | 3.1
Grow capacity of Regional Committees | Identify gaps in regional coordination at the local level | Regional Leads and Regional Committee members | Summer 2012 | 3.1
| Ensure that Regional Committee Leads have approval to spend staff time on Regional Committee coordination | Regional Leads with support of CoC Lead (NCCEH) | Fall 2012 | 3.1
| Identify strategies to fill gaps in Regional Committee coordination at the local level | Regional Leads and CoC Lead (NCCEH) | Fall 2012 | 3.1
Grow CoC Lead Capacity | Identify gaps in capacity | ICCHP, CoC Lead (NCCEH) and BoS CoC Steering Committee members | Summer 2012 | 3.1
| Create plan for addressing gaps | ICCHP, CoC Lead (NCCEH) and BoS CoC Steering Committee members | Fall 2012 | 3.1
| Secure funding and make adjustments | ICCHP, CoC Lead (NCCEH) and BoS CoC Steering Committee members | 2013 | 3.1

## 4-HMIS
Goal Four: Improve HMIS Use and Capacity
Strategy | Action Steps | Person/Organization Responsible | Timeframe | Relevance
|  |  |  | CoC Check-up Elements(s) | FSP Strategy(s) | HEARTH PM(s)
Improve the capacity of the CoC to manage the HMIS responsibilities of the CoC | Hold a meeting with CHIN/HMIS Lead regarding roles and responsibilities | CoC and HMIS Leads (NCCEH and CHIN) | 2012-05-01 | 3.3 | 10c, 2g | A-G
| Draft new language that clarifies the respective roles of the CoC and the HMIS Lead Agency | CoC and HMIS Leads (NCCEH and CHIN) | 2012-05-01
| Approve new MOU with CHIN | Steering Committee | 2012-06-01
Improve HMIS reporting or otherwise informing the CoC decision-making group of data quality concerns | Hold a meeting with HMIS Lead regarding BoS CoC data quality and process of improvement | CoC and HMIS Leads (NCCEH and CHIN) | 2012-04-01 | 3.3.5.3
| Create process for BoS data quality checks at the regional and BoS level | CoC and HMIS Leads (NCCEH and CHIN) | April-May 2012 | 3.3.5.3
| Regional Leads regularly discuss data quality at the regional level | Regional Leads | Summer 2012 | 3.3
| Form a data quality subcommittee and meet quarterly to discuss DQ at the BoS CoC level (to include HMIS Lead participation) | CoC Lead (NCCEH) | 2012-06-01 | 3.3.6
Improve the capacity of the HMIS Lead agency to adequately fulfill its responsibilities | Review HMIS Lead responsibilities | CoC and HMIS Leads (NCCEH and CHIN) | 2012-05-01 | 3.3
| Evaluate gaps in capacity | CoC and HMIS Leads (NCCEH and CHIN) | Summer 2012
| Conduct end-user and community leaders survey of CHIN | NCCEH | Summer 2012
| Create plan for improvement | CoC Lead (NCCEH) and HMIS Lead (CHIN) | Summer 2012
| Support staffing or fee structure changes (if any) | CoC Lead (NCCEH) | Summer 2012 | 3.3.8.1
Improve utility and usefulness of HMIS data for CoC and participating agencies | Conduct end-user and community leaders survey of CHIN | NCCEH | Summer 2012 | 3.3
| Develop HMIS data qualtiy plan | HMIS Lead (CHIN) and CoC Lead | Summer 2012 | 1.1, 1.4, 1.5, 4.1, 4.4
| Make adjustments as needed | HMIS Lead (CHIN) | Fall 2012 | 3.3
| Use HMIS to generate reports for use in monitoring and evaluating system and project performance | CHIN users & funders | Fall 2012 | 3.3.17/3.3.18
Increase AHAR accepted shells | Training from HMIS Lead (CHIN) regarding how to read AHAR reports | HMIS Lead (CHIN) | Summer 2012 | 3.3.24
| Create plan to increase bed coverage for each AHAR category | CoC and HMIS Leads (NCCEH and CHIN) and Steering Committee | 2012-05-01 | 3.3.23
| Increase HMIS bed coverage | Regional Committees and providers | Beginning April 2012, ongoing | 3.3.23
Use HMIS data to generate reports that meaningfully support CoC planning and project development | Evalauate reporting needs | CoC and HMIS Leads (NCCEH and CHIN) and Steering Committee | Begin in 2013 | 3.3
| Create plan to create reports for the CoC | CoC and HMIS Leads (NCCEH and CHIN) and Steering Committee | Begin in 2013
| Begin using HMIS in CoC planning and project development | Steering & Regional Committees | Begin in 2013 | 3.3.22
Use BoS HMIS grant to pay for data analysis | Evaluate BoS data analysis needs | CoC Lead (NCCEH) | Fall 2012 | 3.3
| Create plan on how to meet data analysis needs | CoC and HMIS Leads (NCCEH and CHIN) | Fall 2012
| Begin using BoS HMIS grant for data analysis | CoC Lead and HMIS Lead (NCCEH and CHIN) | 2013-07-01

## 5-Performance
Goal Five: Improve CoC & ESG Grantee Performance
Strategy | Action Steps | Person/Organization Responsible | Timeframe | Relevance
|  |  |  | CoC Check-up Elements(s) | FSP Strategy(s) | HEARTH PM(s)
Provide Education on Evidence-Based Practices | Identify trainging needs | CoC Lead (NCCEH), Regional Leads, and grantees | semi-annually beginning summer 2012 | 3 | 7b, 2c | C
| Make in-person trainings available to providers | NCCEH | ongoing |  | 2h, 1a, 2a | A-G
| Use conference calls and subcommittees to provide training & education |  | ongoing
| Create materials to post online |  | ongoing
Require Grantees to Report on Performance at Regional Committees | Develop reporting format for grantees |  | 2012-05-01
| Regional Committees schedule ESG & CoCs grantees to report on projects at RC meetings on a quarterly basis | Regional Leads | 2012-05-01
| ESG & CoC Grantees present program information based on required format | CoC & ESG Grantees | Ongoing quarterly
| Review and update grantee RC reporting format | CoC Lead (NCCEH) | as needed, minimum annually
Use Quarterly Performance Reports to measure performance on quarterly basis | Complete QPR and submit to NCCEH | CoC grantees | Ongoing quarterly |  |  | C,E
| Review performance check on QPR and make program adjustments as necessary | CoC grantees | Ongoing quarterly |  |  | A-G
| Review QPRs and provide technical assistance as needed | CoC Lead (NCCEH) | Ongoing quarterly
| Review and Update QPR to reflect HEARTH Performance Measurement Questions | CoC Lead (NCCEH) | After HEARTH CoC Regulations are available |  | 10c
Increase understanding and accuracy of HUD Annual Progress Report | Provide APR training | HUD | 2012 |  | 2b
| CoC grantees submit draft APR to NCCEH before | CoC grantees | Ongoing |  | 2a, 2h
| Check for accuracy and completeness of APR | CoC Lead (NCCEH) | Ongoing
| Provide technical assistance to grantees completing APRs as necessary | CoC Lead (NCCEH) | Ongoing
| Create comprehensive Performance Management Plan (integrate APR and systems-level performance monitoring/improvement tasks and HMIS DQ processes and expectations | CoC Lead (NCCEH) and HMIS Lead | 2013 | 1.1, 1.4, 1.5, 4.1, 4.4
| CoC grantees submit corrected APR to HUD | CoC Grantees | Ongoing | 3

## 6-Housing & Services
Goal Six: Improve CoC Housing and Services Capacity
Strategy | Action Steps | Person/Organization Responsible | Timeframe | Relevance
|  |  |  | CoC Check-up Elements(s) | FSP Strategy(s) | HEARTH PM(s)
Improve accessibility of the housing and services in the BoS CoC by persons who are homeless or at-risk of homelessness to improve sufficiency and effetiveness of preventing and ending homelessenss | Inventory housing and services in Regional Committees and create baseline | Regional Committee/ Regional Lead w. support from CoC Lead (NCCEH) | Summer 2013 | 4.1-4.4 | 4a, 3a, 4c, 10a, 10d | A-G
| Create plan to improve accessibility of housing and services in the BoS CoC at the regional level | Regional Committee/ Regional Lead w. support from CoC Lead (NCCEH) | Summer 2013 | 4.1-4.4
| Follow plan and increase housing and services accessibility | Regional Committee/ Regional Lead w. support from CoC Lead (NCCEH) | Summer 2013 | 4.1-4.4
Improve the system of integrated housing and services | Inventory housing and services in Regional Committees and create baseline | Regional Committee/Regional Lead w. support from CoC Lead (NCCEH) | 2013-01-01 | 4.2
Improve the CoC's knowledge and capacity to provide housing and services | Assess current knowledge and capacity | CoC Lead (NCCEH) and Regional Leads | Winter 2012 | 4.4
| Create improvement plan including training and technical assistance | CoC Lead (NCCEH) and Regional Leads | Spring 2013 | 4.4
| Implement Plan | CoC Lead (NCCEH) and Regional Leads | Summer 2013 | 4.4
Improve access to income supports | Continue SOAR training and support | NCCEH | Ongoing | 4 | 6b
| Promote SOAR at the local level | Regional Committees | Ongoing
| Dedicate positions or staff time to SOAR | providers | Ongoing
Prepare for Medicaid expansion | Research opportunities | NCCEH | Winter 2012
| Advocate for targeted resources and adequate service packages | NCCEH with support from communities | Winter 2012
| Educate communities | NCCEEH | 2013 |  | 6e
Expand supply of supportive housing | After assessing Needs & Gaps, create supportive housing expansion plan | Steering Committee | Spring 2013
| Implement Plan | Regional Committees, providers, CoC Lead & funders | Summer 2013 |  | 4a, 4c
Promote best practices in crisis response | Assess current knowledge and capacity | CoC Lead (NCCEH) | Fall 2012
| Create improvement plan including training and technical assistance | CoC Lead (NCCEH) | Winter 2012
| Implement Plan | all stakeholders | 2013 |  | 10a
Support rental housing subsidies | Inventory current stock and research best practice approaches | CoC Lead (NCCEH) with support from Regional Leads | 2013-01-01 |  | 10a, 2a
| Advocate for existing resources to support rental housing subsidies | all stakeholders | Ongoing |  | 3a
| Invest CoC & ESG dollars in rental assistance | grantees, Regional Committee, CoC Lead (NCCEH) | 2012,ongoing |  | 3a
Increase availability of behavioral health services | Advocate for medicaid & IPRS funding for tenancy supports | NCCEH with support from communities | Spring 2012, ongoing |  | 6e
| Provide training on working with homeless & at-risk populations to behavioral health providers | DHHS & NCCEH | Spring 2012, ongoing |  | 7e
Set a path to ending all types of homelessness | Ensure continuity through HPRP services | CoC Lead (NCCEH) and Regional Leads | Ongoing |  | 10d
| Improve access to assistance | CoC Lead (NCCEH) and Regional Leads | Ongoing |  | 3c
| Increase service-enriched housing | CoC Lead (NCCEH) and Regional Leads | Ongoing |  | 3d
| Coordinate/Integrate employment programs, increase work for veterans | CoC Lead (NCCEH) and Regional Leads | Ongoing |  | 5d, 5e
| Inventory Federal emergency response systems | CoC Lead (NCCEH) and Regional Leads | Summer 2013 |  | 2f
| Increase targeted services for persons experiencing homelessness or at-risk of homelessness | CoC Lead (NCCEH) and Regional Leads | Ongoing | 4.1 | 3c, 10a
| Improve discharge practices of the hospital, foster care, and correction systems so none of them release into homelessness | CoC Lead (NCCEH) and Regional Leads | Summer 2013 | 4.1 | 9a
| Improve assessment for persons experiening or at-risk of homelessness to provide appropriate housing placement and services | CoC Lead (NCCEH) and Regional Leads | Summer 2013 | 4.1 | 4a, 3c
| Improve temporary shelter in linking persons who are homeless to permanent housing options and resources | CoC Lead (NCCEH) and Regional Leads | Ongoing | 4.1.6.8
Increase CoC capacity to house chroncially homeless (CH) individuals and families | Ensure full utilization of all PSH units designated for CH | CoC Lead (NCCEH) and Regional Leads | 2013-06-01 | 4.1 | 4a | A,B,C,D
| Identify number of additional PSH units needed for CH individuals and families | CoC Lead (NCCEH) and Regional Leads | 2013-06-01 | 4.1 | 4a | A,B,C,D
Improve Ch access to/receipt of SSI/SSDI and set goal for improvement if needed | Identify proportion of annual PSH participants who do not receive SSI/SSDI and set goal for improvement if needed | CoC Lead (NCCEH) and Regional Leads | 2013-06-01 | 4.1, 4.3 | 6b | B,E
| Identify proportion fo annuual PSH participants who do not receive SNAP (formerly Food Stamps) and set goal for improvement if needed | CoC Lead (NCCEH) and Regional Leads | 2013-06-01 | 4.1, 4.3 | 5b | B,E
Improve data quality relating to chronic homelessness | Create a workflow for capturing and updating chrinic homeless status in HMIS | HMIS Lead/CoC Lead | 2013-01-01 | 3.3 | 2a | A,D
| Identify a baseline for CH | HMIS Lead/CoC Lead | 2013-01-01 | 3.3 | 2a | A,D
| Set measureable goals for reducing chronic homelessness | HMIS Lead/CoC Lead | 2013-01-01 | 3.3 | 4a | A,D
Maintain collaboration with local VA | invite VA rep involvement in BoS CoC Steering Committee | CoC Lead (NCCEH) | 2012-05-01 | 1.3 | 1b | C
| Collaborate with Verans service providers to create stronger linkages for veterans to mainstream homlessness prevention services | CoC Lead (NCCEH) and Regional Leads | 2012-12-01 | 4.1, 4.2, 4.3 | 5b, 6b | C,D,F
Increase CoC capacity to house homeless veterans | Identify strong BoS CoC provider to apply for HUD GPD funds and work with them to submit successful application for Transition-in-Place model | Regional Lead (NCCEH) and Regional Leads | Winter 2012 | 4.1 | 10c | C,D
| Identify the numbner of additional PSH units for vets needed | Regional Lead (NCCEH) and Regional Leads | 2013-06-01 | 4.1 | 4a | A,B,C,D
Improve homeless vets access to SSI/SSDI and other mainstream programs to increase income and stability | Identify proportion of annual homeless vets in PSH who do not receive SSI/SSDI and set goal for improvement | CoC Lead (NCCEH) and Regional Leads | 2013-06-01 | 4.1,4.3 | 6b | B,E
| Identify proportion of annual homeless vets in CoC programs who do not receive SNAP (formerly Food Stamps) and set goal for improvement | CoC Lead (NCCEH) and Regional Leads | 2013-06-01 | 4.1, 4.3 | 5b | B,E
Increase CoC capacity to house homeless families, children, and youth | Ensure full utilization of all PSH units designed for homeless families | CoC Lead (NCCEH) and Regional Leads | 2013-06-01 | 4.1 | 4a | A,B,C,D
| Identify number of additional PSH units needed for homeless families | CoC Lead (NCCEH) and Regional Leads | 2013-06-01 | 4.1 | 4a | A,B,C,D
Improve performance of existing TH programs for families | Ensure existing TH units for homeless families are consistently operating at capacity | CoC Lead (NCCEH) and Regional Leads | Ongoing | 4.1 | 4a | A,B,C,D,G
| Decrease the average length of time TH programs are providing services/rental assistance, to encourage them to serve more families overall in a more cost effective way, where appropriate | CoC Lead (NCCEH) and Regional Leads | 2013-06-01 | 4.1 | 4a | A,B,C,D,G
| Convert TH programs to transition-in-place approaches where feasible and appropriate | CoC Lead (NCCEH) and Regional Leads | 2013-06-01 | 4.1 | 10c | A,B,C,D,G
| Ensure existing TH units for homeless families are successfully moving families into PH | CoC Lead (NCCEH) and Regional Leads | 2013-06-01 | 4.1 | 10a, 10c, 3d | A,B,C,D,G
Improve homeless families access to/receipt of SSI/SSDI and other mainstream programs to increase income and stability | Identify proportion of annual homeless families in PSH who do not receive SSI/SSDI and set goal for improvement | CoC Lead (NCCEH) and Regional Leads | 2013-06-01 | 4.1,4.3 | 6b | A-G