Coordinated Assessment

Elements—defined access, standardized assessment, coordinated referral

Goals—decrease entries into homelessness, decrease time homeless, decrease returns to homelessness, and provide information to right-size our system

Toolkit—Balance of State Coordinated Assessment workgroup is in the process of creating toolkit for Regional Committees to use. Toolkit will include the following:

- Vision Statement

- Guiding principles

- Menu of models

- Common assessment tool

- Governance structure

- Partnership packet

- Sample MOUs and other documents

Timeline

- April/May—workgroup finishes toolkit

- June—toolkit voted on by Steering Committee, develop training materials, toolkit and information sent to Regional Committees

- Summer 2014—Regional workgroups

- Fall 2014—Regional plans due to BoS Coordinated Assessment workgroup

- January 2015—all Coordinated Assessment systems must be up and running